## Big Picture 24-30
When |  |  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Team | Activity | Primarily Maps To | Status
Group Management | Agree WG Project 2030 Activity Scope |  | Due
| Create V&L Project 2030 Planning Regime |  | In Progress
| Establish Teams |  | In Progress
| Review Project 2030 Activity Scope |  | Not yet due
| Succession Planning |  | Not yet due
| Manage Teams |  | In Progress
Survey | Plan, Conduct and Analyse | Pillar 1 - General | In Progress
| Succession Planning |  | Not yet due
Recruit, Retain, Regain | Establish Recovery Champions Network | Pillar 2 - "Effective structures in place to signpost new ringers and lapsed ringers to local ringing centre contacts" Work Stream | In Progress
| Develop RRR Resources |  | In Progress
| Provide RRR Resources |  | Not yet due
| Develop Tinder for Bell Ringers |  | Not yet due
| Deploy & Maintain Tinder for Bell Ringers |  | Not yet due
Leadership Education | Investigate existing leadership resources | Pillar 3 - "All towers have good leaders" Work Stream | In Progress
| Develop leadership education resources |  | In Progress
| Annual National Volunteering Week push |  | In Progress
| Provide RRR leadership education resources |  | Not yet due | [7 empty] | S
| Deliver leadership education packages |  | Not yet due
Development | Material Resources | Pillar 2 - "Regional hubs have adequate teaching resources" Work Stream | In Progress
| Teacher Support |  | Not yet due
| Course packages |  | Not yet due
Regional Courses | NW Course Planning & Delivery | Pillar 2 - "No one meets a barrier to progress" Work Stream | In Progress
| SW Course Planning |  | In Progress
| SW Course Delivery |  | Not yet due
Project 2030 Strategy activities that might be V&L tasks but not planned or indeed certain. | More ringers under 40 attracted | Pillar 1
More young people learn about ringing
Unified marketing/recruiting website
| Unified ringer platform | Pillar 2
Two more residential courses (i.e. 1 + SW)
Summer Schools - at least one per region
Mentoring Scheme
Relaunch of Cast of 1000
Encourage women in ringing
| University Ringing Network | Product Roadmap
Ringing Finance
Facilitate and support YRCA events

## 24-26
When |  |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 0nwards
[5 empty] | Q1/24 | Q2/24 | Q3/24 | Q4/24 | Q1/25 | Q2/25 | Q3/25 | Q4/25 | Q1/26 | Q2/26 | Q3/26 | Q4/26
Team | Topic | Task | Responsible | Status
Group Management | Establish Project 2030 V&L Framework | Agree WG Name with Exec (Exec to promulgate) | Group Lead | Due
|  | Agree WG Activity Scope for Project 2030 with Exec | Group Lead | Due
| Planning | Plan 24-26 | Group Lead | Complete
|  | Develop 2025 Budget | Group Lead | Not yet due
|  | Plan 25-27 | Group Lead | Not yet due
|  | Develop 2026 Budget | Group Lead | Not yet due
|  | Plan 26-28 | Group Lead | Not yet due
|  | Develop 2027 Budget | Group Lead | Not yet due | [12 empty] | …
|  | Plan 27-29 | Group Lead | Not yet due | [12 empty] | …
| Liasion | Form links with ART | Group Lead | In Progress
|  | Form links with YCRA | Group Lead | Not yet due
| Sustain Group | Launch General Volunteer Model & Recruitment Notice | Group Lead | In Progress
|  | Succession Planning | Group Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Hold Quartery Team Lead & Whole Group meetings | Group Lead | In Progress | [12 empty] | …
Survey | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Recruit more Survey Volunteers | Launch Survey Recruitment Campaign | Team Lead | Not yet due
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Structure and task team (Revise Quarterly) | Team Lead | Not yet due | [12 empty] | …
| Conduct | Initial logistical engagement with circa. 6 local associations/societies | Team Lead | In Progress | [12 empty] | …
|  | Data Collection | Team Lead | Not yet due | [12 empty] | …
|  | Chase-Up data | Team Lead | Not yet due | [12 empty] | …
| Analyse | Analyse Results | Team Lead | Not yet due | [12 empty] | …
|  | Brief report for local associations/societies and for CCCBR Executive | Team Lead | Not yet due | [12 empty] | …
|  | Engage with local associations/societies to discuss Results | Team Lead | Not yet due | [12 empty] | …
| Council AGM Report | State of the Nation’ report to highlight common concerns and global trends | Team Lead | Not yet due | [12 empty] | … (2 yearly)
Recruit, Retain, Regain (RRR) | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Recruit more RRR Volunteers | Launch RRR Recruitment Campaign | Team Lead | Not yet due
|  | Appoint new team lead | Group Lead | Not yet due
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Structure and task team (Revise Quarterly) | Team Lead | Not yet due | [12 empty] | …
| Recovery Champions | Develop a Recruitment Champion (RC) Role Profile | Team Lead | In Progress
|  | Set up a Network of RCs | Team Lead | Not yet due
|  | Raise awareness of Network | Team Lead | Not yet due
|  | Seek ex-Recovery Champions as RCs | Team Lead | Not yet due
|  | Seek Territorial Society/Association (TS/A) RCs | Team Lead | Not yet due
|  | Have at least one Recruitment Champion for each TS/A | Team Lead | Not yet due
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Hold Quarterly RC meetings to exchange intelligence | Team Lead | Not yet due | [12 empty] | …
| RRR Resources | Share plans with ART and seek collaboration | Team Lead | In Progress
|  | Attend ART Conference and brief ART members | Team Lead | In Progress
|  | Update the RRR resources in collaboration with ART | Team Lead | Not yet due
|  | Update the RRR Workshop in collaboration with ART | Team Lead | Not yet due
|  | Online meetings to share good RRR practice | Team Lead | Not yet due | [12 empty] | …
|  | Create & maintain online one stop shop for recruitment resources | Team Lead | Not yet due | [12 empty] | …
|  | Promote good RRR practice using ringing print and social media | Team Lead | Not yet due | [12 empty] | …
| Tinder for Bellringers | Review how Ring For the King (RFTK) campaign matched enquiries with teachers | Team Lead | Not yet due
|  | Investigate effectiveness of RFTK and retention record | Team Lead | Not yet due
|  | Explore setting up an online potential recruit to teaching tower service including: | Team Lead | Not yet due
|  | 1. Towers/hubs offering teaching to potential ringers | Team Lead | Not yet due
|  | 2. Directing would be ringers to local tower/hub | Team Lead | Not yet due
|  | Resolve following challenges to: | Team Lead | Not yet due | [12 empty] | …
|  | 1. Monitor success | Team Lead | Not yet due
|  | 2. Ensure Safeguarding measure are in place | Team Lead | Not yet due | [12 empty] | …
|  | 3. Ensure quality of the learning experience | Team Lead | Not yet due | [12 empty] | …
|  | 4. Identify and fill gaps in local coverage | Team Lead | Not yet due | [12 empty] | …
Leadership Education | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Recruit Leadership Volunteers | Launch Leadership Recruitment Campaign | Team Lead | Not yet due
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Structure and task team (Revise Quarterly) | Team Lead | Not yet due | [12 empty] | …
| Learning the Ropes Leadership | Investigate if and where the ART scheme encourages volunteering and leadership | Team Lead | Not yet due
|  | Suggest how encouraging volunteering and leadership can be incorporated into ART | Team Lead | Not yet due
|  | Review volunteering and leadership ART Collaboration | Team Lead | Not yet due | [12 empty] | … (2 yearly)
| National Volunteering Week 1 – 7 June Each Year | Promote awareness | Team Lead | In Progress | [12 empty] | …
|  | Encourage ringers to celebrate the volunteers making a difference | Team Lead | Not yet due | [12 empty] | …
|  | Highlight some key stories | Team Lead | Not yet due | [12 empty] | …
|  | Review level of involvement | Team Lead | Not yet due | [12 empty] | …
| Leadership Information | Identify and ensure that high quality information on the following is available (in collaboration with Stewardship & Management and with ART): | Team Lead | Not yet due | [12 empty] | …
|  | 1. Running a tower | Team Lead | Not yet due
|  | 2. Teaching a learner | Team Lead | Not yet due
|  | 3. Developing ringers | Team Lead | Not yet due
|  | 4. Organising an outing | Team Lead | Not yet due
|  | 5. Other topics for future plans | Team Lead | Not yet due | [12 empty] | …
|  | Point ringers and especially ringing leaders to information sources (Yearly) | Team Lead | Not yet due | [12 empty] | …
| Bitesize Awareness | Identify mini-story ringing leadership topics | Team Lead | Not yet due
|  | Find examples of effective leadership that matches topics | Team Lead | Not yet due | [12 empty] | …
|  | Create and review story copy | Team Lead | Not yet due | [12 empty] | …
|  | Publish stories in wide range of ringing media | Team Lead | Not yet due | [12 empty] | …
|  | Encourage story subjects to provide copy/do interviews with local media | Team Lead | Not yet due | [12 empty] | …
| AGM Leadership Add-On | Scope content based on available leadership information | Team Lead | Not yet due | [12 empty] | ?
|  | Storyboard 1 hour leadership focus | Team Lead | Not yet due | [12 empty] | ?
|  | Offer to AGM 2026 (Note AGM planning starts in earnest a year ahead) | Team Lead | Not yet due | [12 empty] | ?
|  | Develop 1 hour leadership focus | Team Lead | Not yet due | [12 empty] | ?
|  | Deliver at 2026 AGM | Team Lead | Not yet due | [12 empty] | ?
|  | Review interest and consider revising and repeating in even years (Not Survey SoN yrs.) | Team Lead | Not yet due | [12 empty] | ?
| Residential Ringing Courses - 1 hr Session | Explore concept with Residential course teams | Team Lead | Not yet due
|  | Scope content based on available leadership information and AGM Add-On work | Team Lead | Not yet due
|  | Review content with Residential Course Teams | Team Lead | Not yet due
|  | Develop 1 hr session | Team Lead | Not yet due
|  | Deliver as required | Team Lead | Not yet due | [12 empty] | …
|  | Review with Residential course teams (Q3) | Team Lead | Not yet due | [12 empty] | …
|  | Revise as required (Q4&Q1) | Team Lead | Not yet due | [12 empty] | …
Development | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Publications way-ahead | Investigate coordination/merging with Publications WG | Team Lead | Not yet due
|  | Identify barriers | Team Lead | Not yet due
|  | Prepare Recommendations | Team Lead | Not yet due
|  | Submit to Executive | Group Lead | Not yet due
|  | Incorporate way-ahead into 26-28 plan | Team Lead | Not yet due
| Recruit Development Volunteers | Launch Development Recruitment Campaign | Team Lead | Not yet due
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Structure and task team (Revise Quarterly) | Team Lead | Not yet due | [12 empty] | …
| Non-'Publications' development materials | Procure & Sell model bells | Team Lead | In Progress | [12 empty] | …
|  | Procure & Sell Posters | Team Lead | In Progress | [12 empty] | …
|  | Development of further posters (to include Decent Striking) | Team Lead | Not yet due | [12 empty] | …
|  | Planning of other ringing aid | Team Lead | Not yet due | [12 empty] | …
| Identifying and supporting quality teachers | Liaise with ART | Team Lead | Not yet due
|  | Identify quality teachers | Team Lead | Not yet due
|  | Investigate teachers needs | Team Lead | Not yet due
|  | Gap analysis of teacher support material | Team Lead | Not yet due
|  | Develop teacher support material in collaboration with ART | Team Lead | Not yet due
|  | Deliver support material | Team Lead | Not yet due | [12 empty] | …
| Short Courses | Liaise with ART | Team Lead | Not yet due
|  | Identify existing short course material (including those run by Associations/Societies) | Team Lead | Not yet due
|  | Gap analysis of short course material (to include Decent Striking) | Team Lead | Not yet due
|  | Review and revise existing short course material in collaboration with ART | Team Lead | Not yet due
|  | Develop new short course material in collaboration with ART | Team Lead | Not yet due
|  | Provide short course material to Associations/Societies | Team Lead | Not yet due | [12 empty] | …
|  | Provide short course material to individual teachers in collaboration with ART | Team Lead | Not yet due | [12 empty] | …
|  | Deliver short courses if requested | Team Lead | Not yet due | [12 empty] | …
Regional Courses | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Residential Course coordination | Gather dates of known courses and develop calendar: Next year + 1 | Course Co-ord | Not yet due | [12 empty] | …
|  | Negotiate to deconflict dates in similar areas | Course Co-ord | Not yet due | [12 empty] | …
|  | Hold meeting to discuss overall course calendar: Next year + 1 | Course Co-ord | Not yet due | [12 empty] | …
|  | Publish CC Known Course Programme: Next year + 1 | Course Co-ord | Not yet due | [12 empty] | …
| NW Course - The Society for North West Bell Ringing Courses (SNWBRC) | Planning 2024 Course (Managed by SNWBRC - Business as Usual (BAU)) | Team Lead | In Progress
|  | CC Oversight (BAU) | Course Co-ord | In Progress
|  | 2024 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due
|  | Succession Planning | Course Co-ord | Not yet due
|  | Planning 2025 Course (Managed bySNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due
|  | CC Oversight (BAU) | Course Co-ord | Not yet due
|  | 2025 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due
|  | Succession Planning | Course Co-ord | Not yet due
|  | Planning 2026 Course (Managed by SNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due
|  | CC Oversight (BAU) | Course Co-ord | Not yet due
|  | 2026 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due | [12 empty] | …
|  | Succession Planning | Course Co-ord | Not yet due | [12 empty] | …
|  | Planning 2027 Course (Managed by SNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due | [12 empty] | …
|  | CC Oversight (BAU) | Course Co-ord | Not yet due | [12 empty] | …
| Establish SW Course. Further details in SW Residential Statement of Intent (SWRSI) [Time lines to be finalised when course dates are confirmed] | Identify suitable course base | Team Lead | In Progress
|  | Identify possible dates (see SW RSI) | Team Lead | In Progress
|  | Establish Society for South West Bell Ringing Courses (SSWBRC) - To be confirmed | Course Co-ord | Not yet due
|  | Make booking | Team Lead | Not yet due
|  | Enable a SW Guild/associations liaison to promote discounting structure (85% - NW guide) | Team Lead | Not yet due
|  | Enable SW ART liaison to enable ART | Team Lead | Not yet due
|  | Arrange Insurance | Team Lead | Not yet due
|  | CC Oversight | Course Co-ord | In Progress
|  | Decide on costs to helpers and students (course leaders FOC?) guided by NW Course | Team Lead | Not yet due
|  | Treasurer, bank account, payment methods need setting up. | Team Lead | Not yet due
|  | Create Residential Manager and team | Team Lead | Not yet due
|  | Create advertising, marketing and bookings team | Team Lead | Not yet due
|  | Create Education team to recruit course leaders and helpers | Team Lead | Not yet due
|  | Enable Webmaster Create Website! | Team Lead | Not yet due
|  | Arrange Mini ring | Team Lead | Not yet due
|  | Confirm course dates and begin advertising | Team Lead | Not yet due
|  | Safeguarding checks | Team Lead | Not yet due
|  | Decide on, design and procure SW Course Merchandise | Team Lead | Not yet due
|  | Persons with ‘Local’ knowledge to arrange tower bookings | Team Lead | Not yet due
|  | Arrange Handbells | Team Lead | Not yet due
|  | Arrange Theory sessions | Team Lead | Not yet due
|  | 2024/25 Course Managed by SSWBRC? | Team Lead | Not yet due
| SW Course - The Society for South West Bell Ringing Courses (SSWBRC) [Events and Time lines to be finalised when course dates are confirmed] | Succession Planning | Course Co-ord | Not yet due
|  | Planning 2025/26 Course (Managed by SNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due
|  | CC Oversight (BAU) | Course Co-ord | Not yet due
|  | 2025/26 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due
|  | Succession Planning | Course Co-ord | Not yet due | [12 empty] | …
|  | Planning 2026/27 Course (Managed bySNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due | [12 empty] | …
|  | CC Oversight (BAU) | Course Co-ord | Not yet due | [12 empty] | …
|  | 2026/27 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due | [12 empty] | …
Note on C156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fully residential 150 Students, helpers and leaders.
Note on C159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deposit Required

## Colour Coding Key
Key
Status |  | Tasks
Shading | Meaning | Shading | Meaning
| Complete |  | Complete
| In Progress |  | In Progress
| Not started yet |  | Planned Task
| Late against plan |  | Repeating Planned Tasks
| In Project 2030 Strategy but not planned |  | Planned Sub-task
Due