## 24-26
When |  |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 0nwards
[5 empty] | Q1/24 | Q2/24 | Q3/24 | Q4/24 | Q1/25 | Q2/25 | Q3/25 | Q4/25 | Q1/26 | Q2/26 | Q3/26 | Q4/26
Team | Topic | Task | Responsible | Status
Group Management | Establish Project 2030 V&L Framework | Agree WG Name with Exec (Exec to promulgate) | Group Lead | Complete
|  | Agree WG Activity Scope for Project 2030 with Exec | Group Lead | Complete
| Planning | Plan 24-26 | Group Lead | Complete
|  | Develop 2025 Budget | Group Lead | Due
|  | Plan 25-27 | Group Lead | In Progress
|  | Develop 2026 Budget | Group Lead | Not yet due
|  | Plan 26-28 | Group Lead | Not yet due
|  | Develop 2027 Budget | Group Lead | Not yet due | [12 empty] | …
|  | Plan 27-29 | Group Lead | Not yet due | [12 empty] | …
| Liasion | Form links with ART | Group Lead | In Progress
|  | Form links with YCRA | Group Lead | Complete
| Sustain Group | Launch General Volunteer Model & Recruitment Notice | Group Lead | In Progress
|  | Succession Planning | Group Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Hold Quartery Team Lead & Whole Group meetings | Group Lead | In Progress | [12 empty] | …
Survey | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Recruit more Survey Volunteers | Launch Survey Recruitment Campaign | Team Lead | Complete
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Structure and task team (Revise Quarterly) | Team Lead | Complete | [12 empty] | …
| Conduct | Initial logistical engagement with circa. 6 local associations/societies | Team Lead | In Progress | [12 empty] | …
|  | Data Collection | Team Lead | Not yet due | [12 empty] | …
|  | Chase-Up data | Team Lead | Not yet due | [12 empty] | …
| Analyse | Analyse Results | Team Lead | Not yet due | [12 empty] | …
|  | Brief report for local associations/societies and for CCCBR Executive | Team Lead | Not yet due | [12 empty] | …
|  | Engage with local associations/societies to discuss Results | Team Lead | Not yet due | [12 empty] | …
| Council AGM Report | State of the Nation’ report to highlight common concerns and global trends | Team Lead | Not yet due | [12 empty] | … (2 yearly)
Recruit, Retain, Regain | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Recruit more RRR Volunteers | Launch RRR Recruitment Campaign | Team Lead | Not yet due
|  | Appoint new team lead | Group Lead | Not yet due
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Structure and task team (Revise Quarterly) | Team Lead | Not yet due | [12 empty] | …
| Recovery Champions | Develop a Recruitment Champion (RC) Role Profile | Team Lead | In Progress
|  | Set up a Network of RCs | Team Lead | Not yet due
|  | Raise awareness of Network | Team Lead | Not yet due
|  | Seek ex-Recovery Champions as RCs | Team Lead | Not yet due
|  | Seek Territorial Society/Association (TS/A) RCs | Team Lead | Not yet due
|  | Have at least one Recruitment Champion for each TS/A | Team Lead | Not yet due
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Hold Quarterly RC meetings to exchange intelligence | Team Lead | Not yet due | [12 empty] | …
| RRR Resources | Share plans with ART and seek collaboration | Team Lead | In Progress
|  | Attend ART Conference and brief ART members | Team Lead | In Progress
|  | Update the RRR resources in collaboration with ART | Team Lead | Not yet due
|  | Update the RRR Workshop in collaboration with ART | Team Lead | Not yet due
|  | Online meetings to share good RRR practice | Team Lead | Not yet due | [12 empty] | …
|  | Create & maintain online one stop shop for recruitment resources | Team Lead | Not yet due | [12 empty] | …
|  | Promote good RRR practice using ringing print and social media | Team Lead | Not yet due | [12 empty] | …
| Tinder for Bellringers | Review how Ring For the King (RFTK) campaign matched enquiries with teachers | Team Lead | Not yet due
|  | Investigate effectiveness of RFTK and retention record | Team Lead | Not yet due
|  | Explore setting up an online potential recruit to teaching tower service including: | Team Lead | Not yet due
|  | 1. Towers/hubs offering teaching to potential ringers | Team Lead | Not yet due
|  | 2. Directing would be ringers to local tower/hub | Team Lead | Not yet due
|  | Resolve following challenges to: | Team Lead | Not yet due | [12 empty] | …
|  | 1. Monitor success | Team Lead | Not yet due
|  | 2. Ensure Safeguarding measure are in place | Team Lead | Not yet due | [12 empty] | …
|  | 3. Ensure quality of the learning experience | Team Lead | Not yet due | [12 empty] | …
|  | 4. Identify and fill gaps in local coverage | Team Lead | Not yet due | [12 empty] | …
Leadership Education | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Recruit Leadership Volunteers | Launch Leadership Recruitment Campaign | Team Lead | Complete
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Structure and task team (Revise Quarterly) | Team Lead | Not yet due | [12 empty] | …
| Learning the Ropes Leadership | Investigate if and where the ART scheme encourages volunteering and leadership | Team Lead | Due
|  | Suggest how encouraging volunteering and leadership can be incorporated into ART | Team Lead | Not yet due
|  | Review volunteering and leadership ART Collaboration | Team Lead | Not yet due | [12 empty] | … (2 yearly)
| National Volunteering Week 1 – 7 June Each Year | Promote awareness | Team Lead | Complete | [12 empty] | …
|  | Encourage ringers to celebrate the volunteers making a difference | Team Lead | Complete | [12 empty] | …
|  | Highlight some key stories | Team Lead | Complete | [12 empty] | …
|  | Review level of involvement | Team Lead | Not yet due | [12 empty] | …
| Leadership Information | Identify and ensure that high quality information on the following is available (in collaboration with Stewardship & Management and with ART): | Team Lead | Not yet due | [12 empty] | …
|  | 1. Running a tower | Team Lead | Not yet due
|  | 2. Teaching a learner | Team Lead | Not yet due
|  | 3. Developing ringers | Team Lead | Not yet due
|  | 4. Organising an outing | Team Lead | Not yet due
|  | 5. Other topics for future plans | Team Lead | Not yet due | [12 empty] | …
|  | Point ringers and especially ringing leaders to information sources (Yearly) | Team Lead | Not yet due | [12 empty] | …
| Bitesize Awareness | Identify mini-story ringing leadership topics | Team Lead | Not yet due
|  | Find examples of effective leadership that matches topics | Team Lead | Not yet due | [12 empty] | …
|  | Create and review story copy | Team Lead | Not yet due | [12 empty] | …
|  | Publish stories in wide range of ringing media | Team Lead | Not yet due | [12 empty] | …
|  | Encourage story subjects to provide copy/do interviews with local media | Team Lead | Not yet due | [12 empty] | …
| AGM Leadership Add-On | Scope content based on available leadership information | Team Lead | Not yet due | [12 empty] | ?
|  | Storyboard 1 hour leadership focus | Team Lead | Not yet due | [12 empty] | ?
|  | Offer to AGM 2026 (Note AGM planning starts in earnest a year ahead) | Team Lead | Not yet due | [12 empty] | ?
|  | Develop 1 hour leadership focus | Team Lead | Not yet due | [12 empty] | ?
|  | Deliver at 2026 AGM | Team Lead | Not yet due | [12 empty] | ?
|  | Review interest and consider revising and repeating in even years (Not Survey SoN yrs.) | Team Lead | Not yet due | [12 empty] | ?
| Residential Ringing Courses - 1 hr Session | Explore concept with Residential course teams | Team Lead | Not yet due
|  | Scope content based on available leadership information and AGM Add-On work | Team Lead | Not yet due
|  | Review content with Residential Course Teams | Team Lead | Not yet due
|  | Develop 1 hr session | Team Lead | Not yet due
|  | Deliver as required | Team Lead | Not yet due | [12 empty] | …
|  | Review with Residential course teams (Q3) | Team Lead | Not yet due | [12 empty] | …
|  | Revise as required (Q4&Q1) | Team Lead | Not yet due | [12 empty] | …
Development | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Publications way-ahead | Investigate coordination/merging with Publications WG | Team Lead | Complete
|  | Identify barriers | Team Lead | Complete
|  | Prepare Recommendations | Team Lead | Not yet due
|  | Submit to Executive | Group Lead | Not yet due
|  | Incorporate way-ahead into 26-28 plan | Team Lead | Not yet due
| Recruit Development Volunteers | Launch Development Recruitment Campaign | Team Lead | In Progress
|  | Succession Planning | Team Lead | Not yet due | [12 empty] | … (2 yearly)
|  | Structure and task team (Revise Quarterly) | Team Lead | Not yet due | [12 empty] | …
| Non-'Publications' development materials | Procure & Sell model bells | Team Lead | In Progress | [12 empty] | …
|  | Procure & Sell Posters | Team Lead | In Progress | [12 empty] | …
|  | Development of further posters (to include Decent Striking) | Team Lead | Due | [12 empty] | …
|  | Planning of other ringing aids | Team Lead | Not yet due | [12 empty] | …
| Identifying and supporting quality teachers | Liaise with ART | Team Lead | In Progress
|  | Identify quality teachers | Team Lead | In Progress
|  | Investigate teachers needs | Team Lead | Not yet due
|  | Gap analysis of teacher support material | Team Lead | Not yet due
|  | Develop teacher support material in collaboration with ART | Team Lead | Not yet due
|  | Deliver support material | Team Lead | Not yet due | [12 empty] | …
| Short Courses | Liaise with ART | Team Lead | Not yet due
|  | Identify existing short course material (including those run by Associations/Societies) | Team Lead | Not yet due
|  | Gap analysis of short course material (to include Decent Striking) | Team Lead | Not yet due
|  | Review and revise existing short course material in collaboration with ART | Team Lead | Not yet due
|  | Develop new short course material in collaboration with ART | Team Lead | Not yet due
|  | Provide short course material to Associations/Societies | Team Lead | Not yet due | [12 empty] | …
|  | Provide short course material to individual teachers in collaboration with ART | Team Lead | Not yet due | [12 empty] | …
|  | Deliver short courses if requested | Team Lead | Not yet due | [12 empty] | …
Regional Courses | Planning | Plan 24-26 | Team Lead | Complete
|  | Plan 25-27 | Team Lead | Not yet due
|  | Plan 27-28 | Team Lead | Not yet due | [12 empty] | …
| Residential Course coordination | Gather dates of known courses and develop calendar: Next year + 1 | Course Co-ord | Not yet due | [12 empty] | …
|  | Negotiate to deconflict dates in similar areas | Course Co-ord | Not yet due | [12 empty] | …
|  | Hold meeting to discuss overall course calendar: Next year + 1 | Course Co-ord | Not yet due | [12 empty] | …
|  | Publish CC Known Course Programme: Next year + 1 | Course Co-ord | Not yet due | [12 empty] | …
| NW Course - The Society for North West Bell Ringing Courses (SNWBRC) | Planning 2024 Course (Managed by SNWBRC - Business as Usual (BAU)) | Team Lead | In Progress
|  | CC Oversight (BAU) | Course Co-ord | In Progress
|  | 2024 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due
|  | Succession Planning | Course Co-ord | Not yet due
|  | Planning 2025 Course (Managed bySNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due
|  | CC Oversight (BAU) | Course Co-ord | Not yet due
|  | 2025 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due
|  | Succession Planning | Course Co-ord | Not yet due
|  | Planning 2026 Course (Managed by SNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due
|  | CC Oversight (BAU) | Course Co-ord | Not yet due
|  | 2026 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due | [12 empty] | …
|  | Succession Planning | Course Co-ord | Not yet due | [12 empty] | …
|  | Planning 2027 Course (Managed by SNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due | [12 empty] | …
|  | CC Oversight (BAU) | Course Co-ord | Not yet due | [12 empty] | …
| Establish SW Course. Further details in SW Residential Statement of Intent (SWRSI) [Time lines to be finalised when course dates are confirmed] | Identify suitable course base | Team Lead | Complete
|  | Identify possible dates (see SW RSI) | Team Lead | Complete
|  | Establish Society for South West Bell Ringing Courses (SSWBRC) - To be confirmed | Course Co-ord | Not yet due
|  | Make booking | Team Lead | Not yet due
|  | Enable a SW Guild/associations liaison to promote discounting structure (85% - NW guide) | Team Lead | Not yet due
|  | Enable SW ART liaison to enable ART | Team Lead | Not yet due
|  | Arrange Insurance | Team Lead | Not yet due
|  | CC Oversight | Course Co-ord | In Progress
|  | Decide on costs to helpers and students (course leaders FOC?) guided by NW Course | Team Lead | Not yet due
|  | Treasurer, bank account, payment methods need setting up. | Team Lead | Not yet due
|  | Create Residential Manager and team | Team Lead | Not yet due
|  | Create advertising, marketing and bookings team | Team Lead | Not yet due
|  | Create Education team to recruit course leaders and helpers | Team Lead | Not yet due
|  | Enable Webmaster Create Website! | Team Lead | Not yet due
|  | Arrange Mini ring | Team Lead | Not yet due
|  | Confirm course dates and begin advertising | Team Lead | Not yet due
|  | Safeguarding checks | Team Lead | Not yet due
|  | Decide on, design and procure SW Course Merchandise | Team Lead | Not yet due
|  | Persons with ‘Local’ knowledge to arrange tower bookings | Team Lead | Not yet due
|  | Arrange Handbells | Team Lead | Not yet due
|  | Arrange Theory sessions | Team Lead | Not yet due
|  | 2024/25 Course Managed by SSWBRC? | Team Lead | Not yet due
| SW Course - The Society for South West Bell Ringing Courses (SSWBRC) [Events and Time lines to be finalised when course dates are confirmed] | Succession Planning | Course Co-ord | Not yet due
|  | Planning 2025/26 Course (Managed by SNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due
|  | CC Oversight (BAU) | Course Co-ord | Not yet due
|  | 2025/26 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due
|  | Succession Planning | Course Co-ord | Not yet due | [12 empty] | …
|  | Planning 2026/27 Course (Managed bySNWBRC - Business as Usual (BAU)) | Team Lead | Not yet due | [12 empty] | …
|  | CC Oversight (BAU) | Course Co-ord | Not yet due | [12 empty] | …
|  | 2026/27 Course Managed by SNWBRC - BAU) | Team Lead | Not yet due | [12 empty] | …
Note on F2: Paul Wotton: Q1/24 progress noted
Note on G2: Paul Wotton: Q2/24 progress noted
Note on H2: Paul Wotton: Q2/24 update in progress
Note on A4: Paul Wotton: Q2/24 progress noted
Note on F17: Paul Wotton 9 April 2024: Team Leaders meeting held Date not records. Group meeting held 18 February 2024. Notes available.
Note on G17: Paul Wotton: am Lead meeting held 26 May: Notes to be issued Group Meeting to be held 14th July
Note on A19: Paul Wotton: Q2/24 progress requested - No reply
Note on F19: Paul Wotton 9 April 2024: Done - See TL Planning inputs folder.
Note on F25: From Tristan Lockheart 15 Apr 2024: I’ve got a meeting in the calendar with Joe Waters to kickstart the review process for the previous survey, after several failed attempts to find a time which works for both of us. Unfortunately, attempts to get in touch with Martin Jones have not been fruitful but I am continuing attempts to get in touch with him. I am reluctant to progress things further until I know I’ve got reliable backup but will get in touch with the relevant associations once I’ve arranged this. So for now, no progress for my item. Longer term, I think the end of the second phase (i.e., initial results delivered from the second round of associations) would be a good time to install a new leader to take the survey project into the mature phase of the lifestyle, with the focus shifting from project design to project management. This will also line up with an anticipated increase in my commitments pertaining to the Young Ringers workgroup.
Note on A33: Paul Wotton: Q2/24 progress requested - No reply
Note on F33: Paul Wotton 9 April 2024: Done - See TL Planning inputs folder.
Note on F40: From Matt Lawrence 9 April 2024: Role profile- I started drafted one and struggled to make it meaningful. I've come to the conclusion that a call to arms / Recruitment Champions recruitment flyer would be a better product. I will draft one of these ASAP.
Note on F48: From Matt Lawrence 9 April 2024: Liaison with ART - this is up for discussion at the ART Management Committee meeting on Thursday. I'll let you know the outcome.
Note on F49: From Matt Lawrence 9 April 2024: ART Conference - there wasn't space to have a meaningful discussion. Best to role how to involve ART membership into the above and see what other avenues are available.
Note on A66: Paul Wotton: Q2/24 progress noted
Note on F66: Paul Wotton 9 April 2024: Done - See TL Planning inputs folder.
Note on G69: Lucy Chandhail 16 Jul 24: Leadership recruitment - started in that I have contacted Roger Booth and Don who both expressed an interest and I will see what kind of response I get. I also offered people the chance to get involved as part of the articles in the Bellringers group on Facebook and the Ringing World but had no expressions of interest
Note on G72: Lucy Chandhail 16 Jul 24: Learning the Ropes leadership - not yet started but definitely my next task and on my list as the thing to progress over the next three months
Note on F75: From Lucy Chandhial (Team Lead) 2 Apr 24: In Progress I am working on it and still expect to have some content for National Volunteers Week in June. My next step is to ask ART, Ringing World and others to be willing to feature content I can prepare during the National Volunteers Week.
Note on G76: Lucy Chandhail 16 Jul 24: National Volunteering Week - done. Attached is a 'results' summary and it gives me some stories I can use as part of bitesize leadership,
Note on G77: Lucy Chandhail 16 Jul 24: National Volunteering Week - done. Attached is a 'results' summary and it gives me some stories I can use as part of bitesize leadership,
Note on A105: Paul Wotton: Q2/24 progress noted
Note on F105: Paul Wotton 9 April 2024: Done - See TL Planning inputs folder.
Note on G108: Lucy Hopkins Till 16 Jul 24 No longer applicable with demise of publications WG
Note on H109: Lucy Hopkins Till 16 Jul 24 No longer applicable with demise of publications WG
Note on G113: Lucy Hopkins Till 16 Jul 24 I am hoping to get one or two more recruits( ideally to distribute handling posters) through the feelers I am putting out about quality handling teachers.
Note on F116: Lucy Hopkins Till 3 April 24: yes , been dishing out posters and posting off bells
Note on F117: Lucy Hopkins Till 3 April 24: yes , been dishing out posters and posting off bells
Note on G118: Paul Wotton: No progress reported
Note on G120: Lucy Hopkins Till 16 July 24: I emailed Andrew Slade of ART to “liaise” with him but did not receive a reply. I’m not sure there’s any working together we can do regarding teachers anyway ; ART will have their list of teachers and we will have a list of additional recommended teachers.
Note on F135: Paul Wotton 9 April 2024: Done - See TL Planning inputs folder.
Note on F142: Paul Wotton: See David Smith note to cell below.
Note on F143: David Smith 3 April 24: NW planning is IN PROGRESS but there are much greater difficulties than in the past two years, chiefly due to the unavailability of Myerscough. It is planned for 8 to 11 August at Borwick Hall. It is unclear how the changed location and pricing will affect bookings, and there are some other issues.
Note on C156: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fully residential 150 Students, helpers and leaders.
Note on F156: Haley Young 2nd April 24: dentify suitable course base - I think this is complete - Millfield School, Street, Glastonbury - Paul to confirm that accommodation is suitable, but we fully expect it to be.
Note on F157: Haley Young 2nd April 2024: Identify possible dates - I think this is also complete - October half term 2025 - we have a window of 2 weeks at Millfield, I'm just awaiting the county council dates for that half term to be published in order to identify which dates to be exact.
Note on C159: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Deposit Required
Note on F163: David Smith 3 April 24: SW course is IN PROGRESS, as reported by Hayley.

## Colour Coding Key
Key
Status |  | Tasks
Shading | Meaning | Shading | Meaning
| Complete |  | Complete
| In Progress |  | In Progress
| Not started yet |  | Planned Task
| Late against plan |  | Repeating Planned Tasks
| In Project 2030 Strategy but not planned |  | Planned Sub-task
Due

## Big Picture 24-30
When |  |  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Team | Activity | Primarily Maps To | Status
Group Management | Agree WG Project 2030 Activity Scope |  | Complete | bar: 2024
| Create V&L Project 2030 Planning Regime |  | Complete | bar: 2024
| Establish Teams |  | In Progress | bar: 2024
| Review Project 2030 Activity Scope |  | Not yet due | bar: 2025 to 2030
| Succession Planning |  | Not yet due | bar: 2025 to 2030
| Manage Teams |  | In Progress
Survey | Plan, Conduct and Analyse | Pillar 1 - General | In Progress
| Succession Planning |  | Not yet due | bar: 2025 to 2030
Recruit, Retain, Regain | Establish Recovery Champions Network | Pillar 2 - "Effective structures in place to signpost new ringers and lapsed ringers to local ringing centre contacts" Work Stream | In Progress | bar: 2024
| Develop RRR Resources |  | In Progress | bar: 2024 to 2025
| Provide RRR Resources |  | Not yet due | bar: 2025 to 2030
| Develop Tinder for Bell Ringers |  | Not yet due | bar: 2026 to 2028
| Deploy & Maintain Tinder for Bell Ringers |  | Not yet due | bar: 2028 to 2030
Leadership Education | Investigate existing leadership resources | Pillar 3 - "All towers have good leaders" Work Stream | In Progress | bar: 2024
| Develop leadership education resources |  | In Progress | bar: 2024 to 2026
| Annual National Volunteering Week push |  | In Progress
| Provide RRR leadership education resources |  | Not yet due | [7 empty] | S | bar: 2025 to 2030
| Deliver leadership education packages |  | Not yet due | bar: 2026 to 2030
Development | Material Resources | Pillar 2 - "Regional hubs have adequate teaching resources" Work Stream | In Progress
| Teacher Support |  | Not yet due | bar: 2025 to 2030
| Course packages |  | Not yet due | bar: 2026 to 2030
Regional Courses | NW Course Planning & Delivery | Pillar 2 - "No one meets a barrier to progress" Work Stream | In Progress
| SW Course Planning |  | In Progress
| SW Course Delivery |  | Not yet due | bar: 2025 to 2030
Project 2030 Strategy activities that might be V&L tasks but not planned or indeed certain. | Health benefits of ringing research (PW Idea) | Pillar 1
Unified marketing/recruiting website
| Unified ringer platform | Pillar 2
Two more residential courses (i.e. 1 + SW)
Summer Schools - at least one per region
Mentoring Scheme
Relaunch of Cast of 1000