## Big Picture 24-30
When |  |  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
Team | Activity | Primarily Maps To | Status
Governance | Establish Young Ringers Hub team | Pillar 2 | Complete | bar: 2024
| Establish steering group |  | Complete | bar: 2024
| Create governance around BAU steering group |  | Not yet due | bar: 2025
| Merge YCRA and YRH steering groups |  | Complete | bar: 2025
| Create team to maintain and operate |  | Not yet due | bar: 2025
| Young Ringers Hub project remit agreed |  | Complete | bar: 2024
| Reporting requirements agreed |  | Complete | bar: 2024
| Comms plan |  | In Progress | bar: 2024 to 2025
Young Ringers Hub website design | Launch prototype website Sept 24 | Pillar 2 | Complete | bar: 2024
| Beta portal launch Sept 25 |  | In Progress | bar: 2025
| Remit agreed |  | Complete | bar: 2024
Not yet due
Young Ringers Hub under 18s content | Prioritised content development | Pillar 2 | In Progress | bar: 2024 to 2025
| Create team to maintain and operate |  | Not yet due | bar: 2025 to 2026
Not yet due
Young Ringers Hub over 18s content | Prioritised content development | Pillar 2 | In Progress | bar: 2024 to 2025
| Create team to maintain and operate |  | Not yet due | bar: 2025 to 2026
Not yet due
Social Media Strategy | Develop social media strategy | Pillar 2 | In Progress | bar: 2024 to 2025
| Create team to maintain and operate |  | Not yet due | bar: 2025 to 2026
Not yet due
Supporting young ringers | Set out draft proposal to stakeholders | Pillar 2 | Complete | bar: 2024
| Agree proposal with stakeholders |  | In Progress | bar: 2025
| Implement structure |  | Not yet due | bar: 2025 to 2026
| Create team to maintain and operate |  | Not yet due | bar: 2025 to 2026
Aligned activities led by other Workstreams | NHLF funding bid | Pillar 1
Mobile belfries
Targeted recruitment campaigns (R&D)
Branding - marketing collateral
Marketing & recruitment platform (Technology)
| Regional contact hub structure (R&D) | Pillar 2
Ringing skills development (R&D)
Unified ringing platform (technology)
R&D national annual volunteer week push
| Promoting active leadership (R&D) | Pillar 3
Inclusive leadership (CCCBR PR)
Bitesized technical knowledge (Environments)

## 2025-2026
When |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 0nwards
|  |  |  | Q1/24 | Q2/24 | Q3/24 | Q4/24 | Q1/25 | Q2/25 | Q3/25 | Q4/25 | Q1/26 | Q2/26 | Q3/26 | Q4/26
Team | Task | Responsible | Status
Governance | Steering Group established | Andrea | Complete |  |  | 2024-11-10
| Merge YCRA and YRH Steering Groups | Andrea | Complete
| Team leaders CC logins and email addresses | Andrea | Complete
| Lessons learned review from YCRA | Emily | In Progress
| Seek funding required to develop and sustain website | Andrea | Not yet due
Not yet due
Not yet due
Website design | Port Universityringing.com to CCCBR servers | Tristan | Complete
| Set up website branding working group | Andrea | In Progress
| Set up website design working group | Andrea | In Progress
| Create user requirements spec for YCRH and YCRA elements | Tristan | Not yet due
| Define key milestones for website design and delivery | Tristan | Not yet due
| Beta website launch | Tristan | Not yet due
| Establish working group to maintain site | Tristan | Not yet due
| Identify funding requirements for website - development and BAU | Tristan | Not yet due
Not yet due
Not yet due
Under 18s content | Create prioritised content and plan out key milestones below | Jos | In Progress
| Identify resources needed to maintain content (cost and people) | Jos | Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Over 18s content | Create prioritised content and plan out key milestones below | Carys | In Progress
| Identify resources needed to maintain content (cost and people) | Carys | In Progress
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Social Media Strategy | Develop social media strategy | Hana | In Progress
| Create prioritised content and plan out key milestones below | Hana | Not yet due
| Identify resources needed to maintain content (cost and people) | Hana | Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Comms | Ringing world article Oct 24 | Andrea | Complete
| Publish comms plan and set out comms below | Andrea | In Progress
| Exec & WG leads report / update website 22.2 | Andrea | Not yet due
| Exec & WG leads report / update website 24.5 | Andrea | Not yet due
| Exec & WG leads report / update website 30.8 | Andrea | Not yet due
| Exec & WG leads report / update website 8.11 | Andrea | Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Not yet due
Supporting Young Ringers | RWNYC led canvas opinion of youth leaders | Jo C | Complete
| Draft proposals for youth ringing structure shared | Andrea | Complete
| Create proposition for youth ringing structure | Andrea | In Progress
| Create database of youth ringing contacts to be hosted on YCRA | Andrea | In Progress
| Seek approval from Exec & WG leads for youth ringing structure proposal | Andrea | Not yet due
| Create governance to maintain youth ringing structure | Andrea | Not yet due
| Recruit regional YCRA leaders | YCRA | Not yet due
| Identify funding requirements | YCRA | Not yet due
Project Manager | Create data capture process | Jimmy | In Progress
| Collate data content | Jimmy | Not yet due
| Collate funding requirements for development and BAU | Jimmy | Not yet due
Not yet due
Not yet due
Not yet due

## Colour Coding Key
Key
Status |  | Tasks
Shading | Meaning | Shading | Meaning
| Complete |  | Complete
| In Progress |  | In Progress
| Not started yet |  | Planned Task
| Late against plan |  | Due