## Plan
When |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 0nwards
|  |  |  | Q1/24 | Q2/24 | Q3/24 | Q4/24 | Q1/25 | Q2/25 | Q3/25 | Q4/25 | Q1/26 | Q2/26 | Q3/26 | Q4/26
Team | Task / deliverable | Responsible | Status
YOUNG RINGERS HUB
| Team leaders CC logins and email addresses | Andrea | Complete
Website design | Proof of concept | Tristan | In Progress
| Populate new website with available information | Tristan | In Progress
| Beta website launch / PR campaign | Tristan / Andrea | Not yet due
| Order YRH banners to support launch | Andrea | Not yet due
| Establish steering group to update and maintain site | Tristan | Not yet due
| Identify funding requirements for website - development and BAU | Tristan / Andrea | Not yet due
UNIVERSITY RINGING
Website design | Create new University Ringing site and populate | Tristan | In Progress
| Create process for updating site as officers etc change | Tristan | Not yet due
| Link to Young Ringers Hub | Tristan | Not yet due
| Launch new website / PR campaign | Tristan / Andrea | Not yet due
| Order University Ringing banners to support launch | Andrea | Not yet due
University societies | Survey for societies to capture what they do well | Adrian | In Progress
| Create templated guidance from feedback | Andrea / Tristan / Adrian | Not yet due
| Publish guidance on Young Ringers Hub / PR campaign | Tristan / Andrea | Not yet due
| Identify review process and costs of keeping guidance up to date | Tristan | Not yet due
| Use survey outputs / guidance to inform "Supporting Young RIngers" project | Andrea | Not yet due
YOUTH GROUPS (UNDER 18)
Scouts blueprint | Derbyshire scouts / diocese developing proposal | Carole Hallam | In Progress
| Project team to review Derbyshire proposal and propose blueprint | Andrea / Alena | Not yet due
Badge syllabus | CCCBR and Derbyshire team to collaborate on badge syllabus proposal | Andrea / Carole | Not yet due
Youth group guidance | Create stand alone guidance for youth group / school tower visits incl pathways into ringing | Andrea / Alena | Not yet due
| Guidance on how to work with neurodivergent young people | Jos Leggett | In Progress
| Cross reference to School lesson plans to capture relevant info | Andrea | Not yet due
Youth group marketing | Create marketing strategy to support project and events e.g Scout jambourees | Alena / John L | Not yet due
DofE marketing | Marketing of ringing for DofE | Andrea / John L | Not yet due
Handbells for young people | Steph Pendlebury secretary@scacr.org leading group to produce guidance | Steph | In Progress
SCHOOL LESSON PLANS
Plans | Primary lesson plans complete | Jason | In Progress
| Secondary lesson plans complete | Jason | In Progress
| PowerPoint resources in place | Jason | In Progress
| Training materials for teachers | Jason | In Progress
| Lesson plans aligned with mobile belfries | Jason | In Progress
| "what next" information for schools | Jason | In Progress
| Annual refresh process | Jason | In Progress
Roll out | Delivery model in place | Neil Jones | Not yet due
| Prioritised incremental delivery plan in place | Neil Jones | Not yet due
| Marketing and branding strategy in place for roll out and BAU | Neil Jones | Not yet due
| Resource plan for roll out | Neil Jones | Not yet due
| Funding package for roll out in place | Andrea
BAU | Resource plan for BAU | Helen Allton | Not yet due
| Lesson plans available for use | Helen Allton | Not yet due
| Quality control / peer review process in place for roll out and BAU | Helen Allton | Not yet due
| Operating model established on CCCBR website | Helen Allton | Not yet due
| Protocols in place around Safeguarding, H&S, insurance etc | Helen Allton | Not yet due
| Funding package in place to support BAU | Andrea | Not yet due
SUPPORTING YOUNG RINGERS
| Creat proposal for Supporting Young Ringers project and seek stakeholder support | Andrea | In Progress
| Create and share database of youth ringing contacts | Andrea | Not yet due
| Set up communications forum for youth ringing leaders | Andrea | Not yet due
| Recruit regional YCRA leaders | TBC | Not yet due

## Action Log
| ACTION | WHO | RAG STATUS | COMMENTS
YOUNG RINGERS HUB
| Upload existing YCRA guidance to Intermin YRH | Emily / Tristan
| Create "proof of concept" website | Tristan / Martyn
UNIVERSITY RINGING
University societies | Create online form to send to university societies to collate info / best practice | Adrian
| Send out in time for first practice after end exams | Adrian
| Collate data in spreadsheet and share | Adrian
| Create guidance based on what works | Andrea / Tristan
University Ringing website | Update and populate website | Tristan
| Define process for keeping up to date | Tristan
| Link to new YRH website | Tristan
YOUTH GROUPS
| Review feedback from conversations with Carole Hallam & Alena Wardle and draft project remit | Andrea |  | See emails and one note
| Helen Allton to send feedback and materials from Scouts visit | Helen
SCHOOLS
| Contact Bences and Dickon about how we host things for sale / access / fulfillment | Andrea
| Arrange "in action" event | Jason
| Identify potential schools for event | Andrea |  | Email responses sent to Jason
| Handbells in schools guidance | Steph P
| Share example of "off the shelf" curriculum packages | Jason
| Upload lesson plans to OneDrive | Jason |  | Checking
| Contact John Lagdon regarding marketing rep | Andrea |  | john.lagdon@cccbr.org.uk
| Engage with potential scool in DAventry Branch for "in action event" | Helen
| Review plan deliverables as project progresses | ALL
| Arrange review session at Southwark to look at plans in details | Andrea / Jason |  | Invite other volunteers
| Contact Nikki THomas to see what we can learn from MD | Andrea
SUPPORTING YOUNG RINGERS
Brooks
YCRA
COMMS & Governance
| Draft AGM report | Andrea
| Exec & WG leads report / update website 24.5 | Andrea
| Exec & WG leads report / update website 30.8 | Andrea
| Exec & WG leads report / update website 8.11 | Andrea
| Update article for RW and CC | Andrea